## Roadmap
Budgie AI — High-Level Roadmap (v0.2)
Version: 0.2 ¦ Date: 21 April 2026
|  |  |  | Duration range TBA |  |  |  | T -> (T+30) | T->(T+90)
Org. | Lane | Workstream | Description | Foundations | Integrations | Feature Layers | Launch Prep | Launch | First 90 Days | Year 1 | Years 2-3 | Gating? | Depends on | Source
Toptal | Strategy | Market discovery & validation | Ongoing validation of personas, problem, positioning with real users | [10 empty] | MD §1-7
| Strategy | Positioning & messaging finalisation | Lock Financial Coach positioning; retire Personal CFO / Web3 Brain language | [8 empty] | Yes |  | MD §10, GTM §1.2
| Strategy | Pricing & tier boundaries | Decide Basic/Premium split, AI feature allocation, pricing | [10 empty] | MD §9, GTM §2
| Product & Tech | Aggregator decision & integration | Finverse vs hybrid (Finverse + alt); resolve 2FA friction; bank API build | [8 empty] | Yes |  | MD §8.1, Epic 2
| Product & Tech | AI infrastructure (LLM, RAG, tool-aug) | Claude integration, RAG library, calculation tool library, guardrails | [10 empty] | Epic 4.2
| Product & Tech | Onboarding & activation flow | First-launch, progressive disclosure, bank connection, FHS early hook | [9 empty] | Aggregator | Epic 1
| Product & Tech | Budget & expense management | Categorisation, budgets, spending analysis, proactive warnings | [9 empty] | Aggregator | Epic 5
| Product & Tech | Goal planning | Savings & debt-payoff goals, roadmaps, dynamic adjustment | [9 empty] | Epic 2, 5 | Epic 6
| Product & Tech | Financial Health Score | Methodology refinement, calculation, display, score-driven engagement | [9 empty] | Founder methodology docs | Epic 7
| Product & Tech | Ask Anything (NLQ) | User-initiated natural language queries against user data | [9 empty] | AI infra | Epic 8
| Product & Tech | Notifications & proactive engagement | Daily check-ins, weekly coaching sessions, event-driven alerts | [9 empty] | AI infra | Epic 9, MD §4.1
| Product & Tech | Data & privacy infrastructure | Identity, storage, consent framework, PDPA/PDPO compliance | [8 empty] | Yes |  | Epic 12
| Product & Tech | Analytics & instrumentation | Event tracking, funnels, engagement, AI quality metrics | [10 empty] | Epic 14
| Product & Tech | v1.1 capability rollout | Multi-currency, predictive coaching, benchmark comparison, Mandarin, etc. | [9 empty] | MVP launch | Backlog v1.1 items
| Design | User journeys & wireframes | End-to-end user flows, screen-level wireframes, interaction patterns | [8 empty] | Yes |  | Design partner scope
| Design | Budgie character & tone-of-voice | Complete character doc, LLM reproducibility testing, voice guidelines | [8 empty] | Yes |  | Epic 4.1, GTM §8.5
| Design | UI mockups | For front end Developers to implement | [8 empty] | Yes |  | Design partner scope
| Design | Visual design system | Component library, accessibility, mobile patterns | [10 empty] | Design partner scope
Budgie AI | Legal & Compliance | Corporate entity establishment | Legal entity registered; jurisdiction decided (likely Singapore) | [8 empty] | Yes |  | MD §13.5, Epic 13.1
| Legal & Compliance | MAS legal review & engagement | Formal counsel review vs FAA; informal MAS engagement; sandbox assessment | [8 empty] | Yes | Corporate entity | MD §13.1, Epic 13.2
| Legal & Compliance | Terms of Service & Privacy Policy | Drafted, reviewed, integrated into onboarding | [8 empty] | Yes | Legal review | Epic 13.3
| Legal & Compliance | Insurance (professional indemnity) | Professional indemnity and product liability cover | [8 empty] | Yes | Corporate entity | Epic 13.1.3
| Legal & Compliance | HKMA readiness review | Regulatory review against HKMA/SFC ahead of HK launch | [9 empty] | MAS review | MD §13.1.2, GTM §6.3
| Marketing & GTM | Website realignment | Rewrite to Financial Coach positioning; remove advisory/DeFi claims | [8 empty] | Yes | Positioning | GTM §3.3
| Marketing & GTM | Waitlist build | Email capture, referral-to-queue mechanic, launch cohort preparation | [9 empty] | Website, Entity | GTM §3.1
| Marketing & GTM | Social content seeding (Budgie character) | Budgie-in-character social presence; establish character before promotion | [9 empty] | Tone-of-voice | GTM §3.2
| Marketing & GTM | Launch campaign & early access | Phased early-access rollout from waitlist; launch announcements in-character | [9 empty] | Waitlist, Onboarding | GTM §4
| Marketing & GTM | Acquisition expansion & paid testing | Broaden channels; small-scale paid tests to establish CAC | [9 empty] | Analytics, Launch | GTM §5.1
| Marketing & GTM | Referral mechanics | In-app referral flow; instrumented for attribution and optimisation | [9 empty] | Analytics | Epic 10, GTM §5.1
| Marketing & GTM | HK readiness (marketing) | Mandarin content, HK-specific voice testing, pre-HK-launch social presence | [9 empty] | HKMA review | GTM §6.3
| Operations | Support & complaint handling | User support channel, complaint logging, AI-guidance dispute escalation | [8 empty] | Yes |  | Epic 13.6
| Operations | Back-office / admin build | Internal dashboards, RBAC, configuration, Zoho CRM integration | [10 empty] | Epic 15

## Legend & Notes
Legend & How to Read This Roadmap
Lanes
Each row belongs to one lane. Lanes group work by function, not by time.
Strategy | Market, positioning, pricing, commercial direction
Product & Tech | Product build — features, architecture, engineering
Design | User journeys, wireframes, character design, visual system
Legal & Compliance | Corporate, regulatory, insurance, terms & policies
Marketing & GTM | Website, audience, content, launch, acquisition
Operations | Support and back-office
Phases
Time runs left to right across eight phase columns. Durations are relative, not calendar-based — phases describe the state of work, not specific dates.
Foundations | Architectural decisions, data model, identity, infrastructure, core AI framework. Plus non-engineering prerequisites — corporate entity, initial legal review, positioning finalisation — that must be in place before features can be built on top.
Integrations | The external connections. Banking aggregator (Finverse or hybrid), LLM provider, crypto exchange APIs, blockchain data provider, analytics platform, payment processor. Everything that talks to someone else's system.
Feature Layers | The user-facing product. Onboarding, budget and expense management, goals, Financial Health Score, Ask Anything, notifications. What users actually see and use.
Launch Prep | The window after features are built but before public launch. Marketing intensifies, compliance items finalise, waitlist warms, website realignment completes, final QA and legal sign-off.
Launch | First few weeks of real users. Phased early-access rollout from the waitlist, not a single public release.
First 90 Days | Post-launch optimisation — activation, engagement, retention, acquisition channel expansion, paid testing. The window where product-market fit signals emerge.
Year 1 | Scaling what works, rolling out v1.1 capabilities, preparing for Hong Kong.
Years 2-3 | Light direction only — HK active launch, v2+ capabilities, potential B2B2C channel. Will be replanned closer to the time.
Activity indicators (phase column fills)
Primary — this is where the main work on this workstream happens.
Secondary — watching, maintaining, or preparing. Not the main focus but still live.
Empty — not active in this phase.
Gating and dependencies
The "Gating?" column flags hard prerequisites — items that must be complete before dependent workstreams can progress or launch.
The "Depends on" column names the upstream workstreams or artefacts that must land first.
Source
References back to the detailed documents — Market Discovery (MD), Product Backlog (Epic n), or GTM Strategy (GTM §n). Use these to drill into the detail behind any roadmap row.
How to maintain this sheet
• Change a phase fill by selecting the cell and using the paint bucket — copy/paste from an existing Primary or Secondary cell is fastest.
• Keep descriptions short. Detail belongs in the source documents, not here.
• Add rows as new workstreams emerge. Keep the Lane column coloured consistently.
• If a row has no activity in any phase, it should not be on the sheet.